## Summary
Buck Hub — MVP Backlog Summary
Counts pull live from the MVP Backlog sheet (edit there; totals refresh on open/recalc).
Module | Stories | Must | Should | Done | % Done
Authentication & Onboarding
Subscription & Billing
Inventory Management
Media Management
Dashboard & Notifications
Events & Competitions
Settings & Configuration
TOTAL
By status (board columns)
To Do
In Progress
In Review
Blocked
Done

## MVP Backlog
PRD ID | Module | Epic | MoSCoW | Priority | Status | User Story | Estimate (pts) | Assignee | Sprint | Notes
S1 | Authentication & Onboarding | 1.A Account Access | Must | High | To Do | As a new user, I want to create an account with my email and a password, so that I can start using the product.
S2 | Authentication & Onboarding | 1.A Account Access | Must | High | To Do | As a returning user, I want to log in and log out reliably on web and mobile, so that my data stays protected.
S3 | Authentication & Onboarding | 1.A Account Access | Must | High | To Do | As a user, I want to sign up or log in with my Google account, so that I don't have to manage another password.
S4 | Authentication & Onboarding | 1.A Account Access | Must | High | To Do | As a user, I want to reset my password if I forget it, so that I'm never locked out.
S5 | Authentication & Onboarding | 1.A Account Access | Must | High | To Do | As a user, I want my session to stay stable across normal daily use, so that I'm not repeatedly logged out in the field.
S101 | Authentication & Onboarding | 1.A Account Access | Must | High | To Do | As a user, I want to sign up or log in with my Apple account, so that I have a native option on iOS.
S6 | Authentication & Onboarding | 1.A Account Access | Should | Medium | To Do | As a user, I want a "Remember me" option on login, so that I stay signed in on my own device.
S102 | Authentication & Onboarding | 1.A Account Access | Should | Medium | To Do | As a new user, I want to confirm my email with a one-time code after signing up, so that my account is verified.
S9 | Authentication & Onboarding | 1.B Operation Setup Wizard | Must | High | To Do | As a new Owner/Rancher, I want a short setup step asking my name, ranch/organization, and state (phone optional), so that the product is set up the right way for me.
S10 | Authentication & Onboarding | 1.B Operation Setup Wizard | Must | High | To Do | As a new user, I want the setup to be a clear, numbered, multi-step flow (plan → operation → inventory) with visible progress, so that I always know how far along I am.
S11 | Authentication & Onboarding | 1.B Operation Setup Wizard | Must | High | To Do | As a new user, I want a confirmation screen after setup ("You're in!") that summarizes my plan and points me to set up my profile, so that I feel confident the setup worked.
S12 | Authentication & Onboarding | 1.B Operation Setup Wizard | Should | Medium | To Do | As a new user, I want to be told I can add more ranches and locations later, so that I don't feel I must get everything perfect up front.
S13 | Authentication & Onboarding | 1.C Initial Roster Import | Must | High | To Do | As a new user, I want an onboarding step to upload my spreadsheet (CSV/Excel or a Google Sheets export) to import my roster, so that I don't have to add animals one by one.
S14 | Authentication & Onboarding | 1.C Initial Roster Import | Must | High | To Do | As a new user, I want to Skip the import step and add animals individually later, so that a messy spreadsheet never blocks me from getting started.
S103 | Authentication & Onboarding | 1.C Initial Roster Import | Should | Medium | To Do | As a new user, after import I want a summary that surfaces any detected co-owners/investors in my sheet and lets me send them invites in one step, so that partners get connected right away.
S16 | Subscription & Billing | 2.A Plan Selection | Must | High | To Do | As a user, I want plans to clearly show the yearly charge (with the monthly equivalent) and that I can upgrade anytime, so that I understand the real commitment before paying.
S18 | Subscription & Billing | 2.A Plan Selection | Must | High | To Do | As a user, I want to toggle between the Owner and Partner plan views, so that I see the pricing relevant to my role.
S115 | Subscription & Billing | 2.A Plan Selection | Must | High | To Do | As a hesitant new user, I want a 30-day free trial before I'm charged, so that I can evaluate the product before committing.
S20 | Subscription & Billing | 2.B Checkout & Payment | Must | High | To Do | As a user, I want to confirm my subscription and pay by card, so that I can activate my plan.
S21 | Subscription & Billing | 2.B Checkout & Payment | Must | High | To Do | As a user, I want a fast in-app payment — Apple in-app purchase on iOS, or card/Apple Pay on Android & web — so that checkout is quick on my device.
S22 | Subscription & Billing | 2.B Checkout & Payment | Must | High | To Do | As a user, I want a clear summary of what I'm paying ("Pro plan — $99, billed yearly") and reassurance I can cancel anytime, so that I pay with confidence.
S23 | Subscription & Billing | 2.B Checkout & Payment | Must | High | To Do | As a user, I want a receipt sent to my email after payment, so that I have a record.
S24 | Subscription & Billing | 2.B Checkout & Payment | Must | High | To Do | As a user, I want a "Go back" option at checkout, so that I can change my plan before paying.
S25 | Subscription & Billing | 2.C Usage Limits & Upgrades | Must | High | To Do | As a user, I want to see how many active animals I'm using against my plan limit (e.g., "47 / 200") with a usage bar, so that I know how much room I have.
S26 | Subscription & Billing | 2.C Usage Limits & Upgrades | Must | High | To Do | As a user, when I approach or exceed my active-animal limit I want to be alerted and prompted to upgrade — but never blocked; the action proceeds and any overage is added to my next bill.
S27 | Subscription & Billing | 2.C Usage Limits & Upgrades | Must | High | To Do | As a user, I want to change my plan from settings, so that I can upgrade as my herd grows.
S28 | Subscription & Billing | 2.C Usage Limits & Upgrades | Should | Medium | To Do | As a user, I want to see my other usage (media storage used, number of team members), so that I understand the full picture of my account.
S29 | Inventory Management | 3.A Roster & Search | Must | High | To Do | As a user, I want to see a list of all animals I have access to immediately after login, so that the inventory is my home base.
S30 | Inventory Management | 3.A Roster & Search | Must | High | To Do | As a user, I want each animal to appear once and be easy to recognize at a glance (name + Brand ID), so that I trust the list.
S31 | Inventory Management | 3.A Roster & Search | Must | High | To Do | As a user, I want to search the roster by name, Brand ID, and other key fields, so that I can find an animal without scrolling.
S32 | Inventory Management | 3.A Roster & Search | Must | High | To Do | As a user, I want to filter the roster by Type and Status (and more filters), so that I can narrow to the animals I care about.
S33 | Inventory Management | 3.A Roster & Search | Must | High | To Do | As a user, I want a roster header summary (e.g., "47 animals on your roster · 39 active · 8 inactive"), so that I understand my herd at a glance.
S34 | Inventory Management | 3.A Roster & Search | Must | High | To Do | As a user, I want the roster to stay fast and paginated with both small and large numbers of animals, so that performance never gets in my way.
S35 | Inventory Management | 3.A Roster & Search | Should | Medium | To Do | As a user, I want to export my roster, so that I can use the data outside the product when needed.
S36 | Inventory Management | 3.B Add & Edit Animals | Must | High | To Do | As a user, I want to add a single animal quickly on web or mobile, where the only required fields are Brand ID and birth date, so that I can do it without help.
S37 | Inventory Management | 3.B Add & Edit Animals | Must | High | To Do | As a user, I want a newly added animal to appear in my inventory immediately, so that I trust it was saved.
S38 | Inventory Management | 3.B Add & Edit Animals | Must | High | To Do | As a user, I want to edit an animal's details later, so that the record stays accurate over time.
S39 | Inventory Management | 3.B Add & Edit Animals | Must | High | To Do | As a user, I want to record ownership and partnership for an animal (primary owner and ownership percentages), so that everyone's stake is documented.
S104 | Inventory Management | 3.B Add & Edit Animals | Must | High | To Do | As a user, I want to set whether the animal is a cow or a bull and optionally record its ABBI number, so that the record reflects sex and registry identity.
S40 | Inventory Management | 3.C Animal Profile (System of Record) | Must | High | To Do | As a user, I want selecting an animal to open a dedicated profile, so that I have one place for everything about it.
S41 | Inventory Management | 3.C Animal Profile (System of Record) | Must | High | To Do | As a user, I want the profile header to show the animal's name, Brand ID, status, and a hero image, so that I instantly recognize the animal.
S42 | Inventory Management | 3.C Animal Profile (System of Record) | Must | High | To Do | As a user, I want an Ownership section showing each owner, their role, and their ownership percentage, so that every stake is clear at a glance.
S43 | Inventory Management | 3.C Animal Profile (System of Record) | Must | High | To Do | As a user, I want a Lineage section showing sire and dam, so that I and my partners can review bloodline.
S95 | Inventory Management | 3.C Animal Profile (System of Record) | Must | High | To Do | As a user, I want the profile to be the anchor for all of that animal's media, with a Recent media gallery and a "view all", so that media never gets disconnected from the animal.
S96 | Inventory Management | 3.C Animal Profile (System of Record) | Must | High | To Do | As a user, I want the profile to remain consistent and identifiable over time, even when ownership changes, so that history is never lost.
S97 | Inventory Management | 3.C Animal Profile (System of Record) | Should | Medium | To Do | As a user, I want a Performance section with a headline score, so that I can gauge the animal's standing quickly.
S98 | Inventory Management | 3.C Animal Profile (System of Record) | Should | Medium | To Do | As a user, I want a Competition history list (event, date, score) on the profile, so that I can follow how the animal has performed.
S99 | Inventory Management | 3.C Animal Profile (System of Record) | Should | Medium | To Do | As a user, I want a Notes & comments thread on the profile, so that stakeholders can discuss the animal in context (ties to Story 64).
S100 | Inventory Management | 3.C Animal Profile (System of Record) | Should | Medium | To Do | As a user, I want a quick-actions rail on the profile (add event, update status, upload media), so that I can act without leaving the page.
S45 | Inventory Management | 3.D Bulk Import | Must | High | To Do | As a user, I want a guided template that tells me what columns are expected, so that my spreadsheet imports cleanly.
S46 | Inventory Management | 3.D Bulk Import | Must | High | To Do | As a user, I want the system to flag duplicate or colliding Brand IDs during import and let me resolve them, so that I don't create conflicting records.
S47 | Inventory Management | 3.D Bulk Import | Must | High | To Do | As a user, I want to see which rows imported successfully and which need attention, so that I trust the result and can fix problems.
S48 | Inventory Management | 3.D Bulk Import | Should | Medium | To Do | As a user, I want to import from both the onboarding wizard and from inside Inventory later, so that I can grow my roster anytime.
S49 | Inventory Management | 3.E Bulk Actions & Lifecycle | Must | High | To Do | As a user, I want to multi-select animals and update their status in bulk, so that I can manage the herd efficiently.
S50 | Inventory Management | 3.E Bulk Actions & Lifecycle | Must | High | To Do | As a user, I want to multi-select animals to add tags, add them to an event, or change their location in bulk, so that I save time on repetitive actions.
S105 | Inventory Management | 3.E Bulk Actions & Lifecycle | Must | High | To Do | As a user, I want my multi-select to persist as I move between paginated pages, so that I can act on a large set without losing my selection.
S51 | Inventory Management | 3.E Bulk Actions & Lifecycle | Must | High | To Do | As a user, I want sold/retired animals to remain viewable as "ghost inventory" rather than disappearing, so that I keep their history.
S52 | Inventory Management | 3.E Bulk Actions & Lifecycle | Must | High | To Do | As a user, I want system-critical statuses (Active, Sold, Retired, In Care/Inactive) to be protected from deletion, so that the lifecycle stays consistent.
S53 | Media Management | 4.A Capture & Upload | Must | High | To Do | As a rancher, I want to capture photos and videos with a point-and-shoot camera directly in the app, so that I don't fill up my personal phone storage.
S54 | Media Management | 4.A Capture & Upload | Must | High | To Do | As a user, I want to upload photos and videos and add external links (YouTube/Instagram/URL) as media, from web and mobile, so that I can add media however I work.
S55 | Media Management | 4.A Capture & Upload | Must | High | To Do | As a user, I want each piece of media to be associated with the correct animal, so that it's never orphaned.
S106 | Media Management | 4.A Capture & Upload | Must | High | To Do | As a user, I want to delete media I've uploaded, so that I can remove mistakes or unwanted items.
S56 | Media Management | 4.B Offline Reliability | Must | High | To Do | As a rancher in a pasture with no signal, I want my captured media and its details saved to a local retry queue, so that nothing is lost.
S57 | Media Management | 4.B Offline Reliability | Must | High | To Do | As a rancher, I want queued media to upload automatically once I'm back in service, so that I don't have to remember to retry.
S58 | Media Management | 4.B Offline Reliability | Must | High | To Do | As a rancher, I want to see the status of pending uploads (queued / uploading / done), so that I trust everything made it.
S59 | Media Management | 4.C Organize & Find | Must | High | To Do | As a user, I want to tag media with the Brand ID and custom tags, so that it's organized and findable.
S60 | Media Management | 4.C Organize & Find | Must | High | To Do | As a user, I want to mark each media item Public or Private, so that I control what partners and owners can see.
S61 | Media Management | 4.C Organize & Find | Must | High | To Do | As a user, I want to browse, search, and filter the media gallery (by animal, Brand ID, type), so that I can find footage quickly.
S62 | Media Management | 4.C Organize & Find | Must | High | To Do | As a user, I want to see all media for a given animal in one place from its profile, so that the animal's record is complete.
S63 | Media Management | 4.C Organize & Find | Should | Medium | To Do | As a user, I want media items to show key context at a glance (animal name, Brand ID, status, owner, date), so that I can scan the gallery efficiently.
S107 | Media Management | 4.C Organize & Find | Should | Medium | To Do | As a user, I want to mark one photo as an animal's favorite/cover image, so that it represents the animal in roster tables.
S108 | Media Management | 4.C Organize & Find | Should | Medium | To Do | As a user, I want to gather a set of media and share the collection with a specific contact from the media page, so that I can send footage to a stakeholder directly.
S64 | Media Management | 4.D Comments | Must | High | To Do | As a partner or owner, I want to leave threaded comments on an animal profile or media item (e.g., "Looks great today!"), so that I can engage without texting the rancher.
S65 | Dashboard & Notifications | 5.A Home Dashboard | Must | High | To Do | As a user, I want a personalized dashboard showing my key metrics (active animals, upcoming events, sold animals), so that I understand my operation at a glance.
S68 | Dashboard & Notifications | 5.A Home Dashboard | Must | High | To Do | As a new user, I want a Day-1 welcome and a setup checklist, so that I know what to do to get fully set up.
S69 | Dashboard & Notifications | 5.A Home Dashboard | Must | High | To Do | As a user, I want clear empty states when there's nothing to show, so that the product never feels broken.
S71 | Dashboard & Notifications | 5.A Home Dashboard | Should | Medium | To Do | As a user with more than one location, I want to switch the dashboard's location context, so that I can focus on one operation at a time.
S72 | Dashboard & Notifications | 5.B Stakeholder Notifications | Must | High | To Do | As a rancher, I want stakeholders to be notified automatically when I post public media or a notable update, so that I no longer have to text and email everyone.
S73 | Dashboard & Notifications | 5.B Stakeholder Notifications | Must | High | To Do | As a partner/owner, I want to receive a notification (push, SMS, or email) when there's an update on an animal I'm associated with, so that I stay informed without asking.
S74 | Dashboard & Notifications | 5.B Stakeholder Notifications | Should | Medium | To Do | As a user, I want notifications to respect an animal's Public/Private visibility, so that private media never triggers a broadcast.
S75 | Events & Competitions | 6.A Event Roster | Must | High | To Do | As a user, I want to see upcoming and past events in separate tabs with date, name, location, and associated animals, so that I can plan and review.
S76 | Events & Competitions | 6.A Event Roster | Must | High | To Do | As a user, I want to add an event manually, so that my calendar reflects reality.
S77 | Events & Competitions | 6.A Event Roster | Must | High | To Do | As a user, I want to associate animals with an event (including bulk "add to event" from Inventory), so that I track which animals are competing where.
S78 | Events & Competitions | 6.A Event Roster | Must | High | To Do | As a user, I want to import and export events, so that I can move data in and out efficiently.
S112 | Events & Competitions | 6.A Event Roster | Must | High | To Do | As a user, I want event data pulled in from the external event source (via extraction/scraping), so that I don't have to enter every event by hand.
S79 | Events & Competitions | 6.A Event Roster | Should | Medium | To Do | As a user, I want events to be paginated and searchable, so that a long history stays manageable.
S111 | Events & Competitions | 6.A Event Roster | Should | Medium | To Do | As a mobile user side-scrolling the events table, I want the date column to stay sticky, so that rows stay readable.
S80 | Events & Competitions | 6.B Competition Tracking | Must | High | To Do | As a user, I want to log that an animal competed at an event, so that its participation is recorded.
S81 | Events & Competitions | 6.B Competition Tracking | Must | High | To Do | As a partner/owner, I want competition activity to appear in Recent Activity and on the animal's profile, so that I can follow performance.
S83 | Settings & Configuration | 7.A Profile & Location | Must | High | To Do | As a user, I want to edit my profile (photo, name, contact email), so that my account reflects who I am.
S84 | Settings & Configuration | 7.A Profile & Location | Must | High | To Do | As a user, I want to edit my operation details (name, state, phone, website), so that my operation info is correct.
S113 | Settings & Configuration | 7.A Profile & Location | Must | High | To Do | As a user, I want to manage my locations (the places I keep animals), so that inventory and "change location" reflect reality.
S114 | Settings & Configuration | 7.A Profile & Location | Must | High | To Do | As a user, I want a unique Ranch ID in my settings, so that partners can be linked to my ranch across operations.
S86 | Settings & Configuration | 7.B Roster Taxonomy | Must | High | To Do | As a user, I want to customize animal types (Bull, Cow, Heifer, Calf, Embryos, …), so that the roster matches my operation.
S87 | Settings & Configuration | 7.B Roster Taxonomy | Must | High | To Do | As a user, I want to customize animal statuses, so that the lifecycle labels fit how I work.
S88 | Settings & Configuration | 7.B Roster Taxonomy | Must | High | To Do | As a user, I want to manage bloodlines/custom labels, so that lineage is consistent across my animals.
S89 | Settings & Configuration | 7.B Roster Taxonomy | Must | High | To Do | As a user, I want system-critical statuses and basic types to be protected from deletion, so that core lifecycle behavior stays intact.
S90 | Settings & Configuration | 7.C Partners & Permissions | Must | High | To Do | As a user, I want a partner directory listing everyone with access — their name, email, phone, role, animal count, and status (Active/Pending), so that I know who's involved.
S91 | Settings & Configuration | 7.C Partners & Permissions | Must | High | To Do | As a user, I want to invite partners by email/SMS from the directory, so that I can grant access quickly.
S92 | Settings & Configuration | 7.C Partners & Permissions | Must | High | To Do | As a user, I want roles (Rancher, Owner, Partner) to map to a clear permissions matrix (e.g., partners are read-only and own-only), so that people only see and do what they should.
S93 | Settings & Configuration | 7.C Partners & Permissions | Must | High | To Do | As a user adding an animal, I want to assign an existing partner — or add and invite a new one inline if they're not in the list — so that ownership is captured at the moment I record the animal.
S94 | Settings & Configuration | 7.D Subscription Management | Must | High | To Do | As a user, I want to view and change my subscription and payment method from settings, so that I can manage billing in one place.